## Sheet1
Waktu Simpan | Nomor Kontrak | PI No. | Lokasi Office | Tanggal Utama | Item ke- | Kategori | Uraian Pekerjaan | Jumlah | Satuan | Tanggal Efektif | Catatan
2026-09-20 07:06:56 | 7201250141 | 023/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | PERSONEL ON CALL | Personnel GS in-charge di lokasi pemboran/ wellservices/ workover, personnel in charge | 1 | man-days | 2026-08-08 | Personel GS - Koordinator Lapangan atas Nama Nur Afiata
2026-09-20 07:45:45 | 7201250141 | 022/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-04 | 1 | PERSONEL ON CALL | Personnel GS in-charge di lokasi pemboran/ wellservices/ workover, personnel in charge | 1 | Day | 2026-09-04 | Tenaga Civil Engineer melakukan survey di Lokasi Sumur Senoro 16
2026-09-20 07:45:45 | 7201250141 | 022/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-04 | 2 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 1 | Day | 2026-09-04 | Kendaraan Operasional Double Cabin DN 8890 RG untuk transportasi Survey ke Lokasi
2026-09-20 10:04:59 | 7201250141 | 024A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-09 | 1 | PERSONEL ON CALL | Operator Heavy Equipment (Vacuum Truck) | 1 | Day | 2026-08-09 | Supporting equipment kegiatan Wellservices 2026, Operator Heavy Equipment (Vacuum Truck)
2026-09-21 12:09:22 | 7201250141 | 031/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-09 | 1 | ADDITIONAL CAMP SERVICES | Laundry services | 0 | Kg | 2026-08-09 | ADDITIONAL CAMP SERVICES Laundry services , crew di Lokasi
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 1 | ADDITIONAL CAMP SERVICES | Portacamp - Office Camp, ukuran 40 FT | 0 | Month | 2026-08-09 | Portacamp - Office Camp, ukuran 40 FT Untuk Support Well Services di Lokasi Senoro
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 2 | ADDITIONAL CAMP SERVICES | Portacamp - Living camp,ukuran 40FT (4 sleepers) | 0 | Month | 2026-08-09 | Portacamp - Living camp,ukuran 40FT (4 sleepers) Untuk Support Well Services di Lokasi Senoro
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 3 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Genset, cap min 80 KVA, silent type, include maintenance | 0 | Month | 2026-08-09 | Genset, cap min 80 KVA, silent type, include maintenance, Operasi Shift Siang
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 4 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Genset, cap min 80 KVA, silent type, include maintenance | 0 | Month | 2026-08-09 | Genset, cap min 80 KVA, silent type, include maintenance, Operasi Shift Malam
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 5 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories | 0 | Month | 2026-08-09 | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories Operasi Malam
2026-09-22 10:56:14 | 7201250141 | 025/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-31 | 6 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories | 0 | Month | 2026-08-09 | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories Operasi Malam
2026-09-24 08:24:36 | 7201250141 | 008/BSS-JOB/WS/VII/2026 | Luwuk | 2026-07-06 | 1 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 0 | Day | 2026-07-06 | Kendaraan Operasional Inova DN 1257 CL Support Team JOB Survey Lokasi di Senoro
2026-09-24 09:50:46 | 7201250141 | 033/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Mobilisasi/ Demobilisasi crane min 70 ton to/from Company Wellsite/ Contractor base | 1 | AU | 2026-08-08 | Mobilisasi Crane Mobile Tadano Kapasitas 70 ton dari Workshop di Lamo ke Cluster B
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | PERSONEL ON CALL | Operator Crane | 1 | man-days | 2026-08-08 | Mulai Tanggal 08/08/2026 Operator Crane Shift Siang atas nama Rasid A Laugi
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 2 | PERSONEL ON CALL | Operator Crane | 1 | man-days | 2026-08-23 | Mulai Tanggal 23/08/2026 Operator Crane Shift Siang atas nama Wanhar
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 3 | PERSONEL ON CALL | Operator Crane | 1 | man-days | 2026-08-08 | Mulai Tanggal 08/08/2026 Operator Crane Shift Malam atas nama Ilsan Adjedar
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 4 | PERSONEL ON CALL | Rigger | 1 | man-days | 2026-08-08 | Mulai Tanggal 08/08/2026 Rigger Crane Shift Siang atas nama Tison
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 5 | PERSONEL ON CALL | Rigger | 1 | man-days | 2026-08-08 | Mulai Tanggal 08/08/2026 Rigger Crane Shift Malam atas nama Agus Dg Mangata
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 6 | PERSONEL ON CALL | Mechanic/ Electrician | 1 | man-days | 2026-08-09 | Mulai Tanggal 09/08/2026 Mechanic/ Electrician operasikan Mesin Genset dan Lighting Tower atas nama Sugeng
2026-09-30 11:48:13 | 7201250141 | 024/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 7 | PERSONEL ON CALL | Mechanic/ Electrician | 1 | man-days | 2026-08-09 | Mulai Tanggal 09/08/2026 Mechanic/ Electrician operasikan Mesin Genset dan Lighting Tower atas nama Ahmad Dhani
2026-09-30 11:58:30 | 7201250141 | 023A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-08-08 | Supporting equipment kegiatan Wellservices 2026 Welder = Personel HSE Officer ( Gusti Ngurah Dwipayana )
2026-09-30 11:58:30 | 7201250141 | 023A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 2 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-08-08 | Supporting equipment kegiatan Wellservices 2026 Welder = Personel Paramedic ( Melita Bella )
2026-09-30 11:58:30 | 7201250141 | 023A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 3 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-08-08 | Supporting equipment kegiatan Wellservices 2026 Welder = Personel Paramedic ( Widiya Satuwo )
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 1 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-08-07 | Mulai Pekerjaan 07/08/2026 Kendaraan Innova DN 1259 CL Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 2 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-08-07 | Mulai Pekerjaan 07/08/2026 Kendaraan Innova DN 1258 CL Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 3 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-08-07 | Mulai Pekerjaan 07/08/2026 Kendaraan Innova DN 1257 CL Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 4 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-08-11 | Mulai tanggal 11/08/2026 Kendaraan Pajero DN 1904 RA Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 5 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 1 | Day | 2026-08-07 | Mulai tanggal 07/08/2026 Kendaraan Hilux DN 1916 CH Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:10:06 | 7201250141 | 026/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 6 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 1 | Day | 2026-08-08 | Mulai tanggal 08/08/2026 Kendaraan Hilux DN 1917 CH Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:16:43 | 7201250141 | 027/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | crane min 70 ton, call out, (hanya unit) | 1 | Day | 2026-08-08 | Mulai Tanggal 08/08/2026 Crane Tadano 70 ton Untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:16:43 | 7201250141 | 027/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 2 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | crane min 70 ton, call out, (hanya unit) | 1 | Day | 2026-08-23 | Mulai Tanggal 23/08/2026 Crane Sany 100 Ton untuk menggantikan Crane Tadano 70 Ton yang rusak
2026-09-30 12:16:43 | 7201250141 | 027/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 3 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Vacuum Truck , Call out, Cap 5000 ltr c/w vacuum pump & acessories, call out, (hanya unit) | 1 | Day | 2026-08-09 | Mulai Tanggal 09/08/2026 Vacuum Truck 5000 L DN 8806 CH untuk Support Pekerjaan Well Services di Senoro Periode Agustus 2026
2026-09-30 12:24:51 | 7201250141 | 032/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | PERSONEL ON CALL | Helper Local (non Skilled) | 0 | man-days | 2026-08-08 | Mulai Tanggal 08/08/2026 Upah harian Flagman di Lokasi Senoro
2026-10-01 13:44:29 | 7201250141 | 035/BSS-JOB/WS/X/2026 | Luwuk | 2026-08-07 | 1 | PROVISIONAL SUM | At Cost + Fee 15% | 1 | AU | 2026-08-07 | Akomodasi Personel JOB Tomori dan Serco di Hotel King Amear Mulai tanggal 07 Agustus 2026
2026-10-02 09:16:37 | 7201250141 | 036/BSS-JOB/WS/IX/2026 | Luwuk | 2026-08-07 | 1 | ADDITIONAL CAMP SERVICES | Laundry services | 489.8 | Kg | 2026-08-07 | Loundry Untuk Personel JOB dan Serco di Hotel King Amear Mulai tanggal 07 Agustus 2026
2026-10-02 09:41:20 | 7201250141 | 030/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-07 | 1 | PROVISIONAL SUM | At Cost + Fee 15% | 1 | AU | 2026-08-07 | Provsum Akomodasi untuk crew well services di penginapan Yellow Toili Mulai tanggal 07 Agustus 2026
2026-10-03 12:56:07 | 7201250141 | 005/BSS-JOB/WS/V/2026 | Luwuk | 2026-05-18 | 1 | MOVING AIR FREIGHT TRANSPORT | Jabodetabek - Luwuk/ Senoro atau sebaliknya | 0 | Kg | 2026-05-18 | Pengiriman Sample air dari Lokasi Cluster B ke Jakarta
2026-10-03 12:56:07 | 7201250141 | 005/BSS-JOB/WS/V/2026 | Luwuk | 2026-05-18 | 2 | MOVING AIR FREIGHT TRANSPORT | Jasa repacking for Airfreight, estimasi ukuran pallet 100x100x100 cm | 0 | Pallet | 2026-05-18 | Pembuatan Pallet Sample Air (packing Barang)
2026-10-03 12:56:07 | 7201250141 | 005/BSS-JOB/WS/V/2026 | Luwuk | 2026-05-18 | 3 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 0 | Day | 2026-05-18 | Pickup Material di Luwuk tgl 18 Mei 2026 dari Lokasi ke Bandara
2026-10-03 12:56:07 | 7201250141 | 005/BSS-JOB/WS/V/2026 | Luwuk | 2026-05-18 | 4 | PERSONEL ON CALL | Helper Local (Skilled) | 0 | man-days | 2026-05-18 | Personel untuk pengurusan Barang di Luwuk dan Personel untuk pengurusan barang di Jakarta
2026-10-03 12:56:07 | 7201250141 | 005/BSS-JOB/WS/V/2026 | Luwuk | 2026-05-18 | 5 | ESTIMATED SUM | Jasa Transportasi dari dan ke Bandara Jasa transportasi menggunakan Pickup Air Port Cengkareng ke Jabodetabek dan sebaliknya | 0 | Trip | 2026-05-20 | Land transportasi dari bandara Cengkareng ke alamat penerima sample air PT.Haliburton
2026-10-03 13:04:37 | 7201250141 | 011/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-03 | 1 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 0 | Day | 2026-08-03 | Pengambilan Material Pop Joint di Senoro 2 ke Luwuk
2026-10-03 13:04:37 | 7201250141 | 011/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-03 | 2 | MOVING AIR FREIGHT TRANSPORT | Jasa repacking for Airfreight, estimasi ukuran pallet 100x100x100 cm | 0 | Pallet | 2026-08-03 | Pembuatan Pallet untuk Pop Joint
2026-10-03 13:04:37 | 7201250141 | 011/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-03 | 3 | PERSONEL ON CALL | Helper Local (Skilled) | 0 | man-days | 2026-08-03 | Personel Handling di Luwuk-Bandara 1 orang dan Jakarta-Bogor 1 orang
2026-10-03 13:04:37 | 7201250141 | 011/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-03 | 4 | MOVING AIR FREIGHT TRANSPORT | Jabodetabek - Luwuk/ Senoro atau sebaliknya | 0 | Kg | 2026-08-03 | Cargo Barang Air Freight Material Pop Joint yang dikirim
2026-10-03 13:04:37 | 7201250141 | 011/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-03 | 5 | ESTIMATED SUM | Jasa Transportasi dari dan ke Bandara Jasa transportasi menggunakan Pickup Air Port Cengkareng ke Jabodetabek dan sebaliknya | 0 | Trip | 2026-08-04 | Pengiriman barang Pop Joint dari Bandara Cengkareng ke Bogor alamat Lamda Multi Dinamika yard
2026-10-06 10:13:17 | 7201250141 | 040/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | PERSONEL ON CALL | Personnel GS in-charge di lokasi pemboran/ wellservices/ workover, personnel in charge | 1 | Day | 2026-09-01 | Personnel GS - Koordinator Lapangan atas nama Nur Afiata Mulai tanggal 01 September 2026
2026-10-06 10:36:32 | 7201250141 | 041/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-09-01 | Support Kegiatan Well Services di Senoro personel Welder = HSE Officer ( Gusti Ngurah Dwipayana) Mulai tanggal 01 September 2026
2026-10-06 10:36:32 | 7201250141 | 041/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-09-01 | Support Kegiatan Well Services di Senoro personel Welder = Paramedic ( Meliita Bella) Mulai tanggal 01 September 2026
2026-10-06 10:36:32 | 7201250141 | 041/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 3 | PERSONEL ON CALL | Welder (GTAW) | 1 | Day | 2026-09-01 | Support Kegiatan Well Services di Senoro personel Welder = Paramedic ( Widiya Satuo) Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | PERSONEL ON CALL | Operator Crane | 1 | Day | 2026-09-01 | Operator Crane Shift Siang atas Nama Wanhar Renaldi Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | PERSONEL ON CALL | Operator Crane | 1 | Day | 2026-09-01 | Operator Crane Shift Malam atas Nama Ilsan Adjedar Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 3 | PERSONEL ON CALL | Rigger | 1 | Day | 2026-09-01 | RIgger Crane Shift Siang atas Nama Tison Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 4 | PERSONEL ON CALL | Rigger | 1 | Day | 2026-09-01 | Rigger Crane Shift Malam atas Nama Agus Dg Mangata Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 5 | PERSONEL ON CALL | Mechanic/ Electrician | 1 | Day | 2026-09-01 | Operator Mesin Genset dan Ligting Tower Shift Siang atas nama Sugeng Mulai tanggal 01 September 2026
2026-10-06 11:20:59 | 7201250141 | 042/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 6 | PERSONEL ON CALL | Mechanic/ Electrician | 1 | Day | 2026-09-01 | Operator Mesin Genset dan Ligting Tower Shift Siang atas nama Ahmad Dhani Mulai tanggal 01 September 2026
2026-10-06 11:41:57 | 7201250141 | 043/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | PERSONEL ON CALL | Operator Heavy Equipment (Vacuum Truck) | 1 | Day | 2026-09-01 | Driver Vacuum Truck atas nama Wijayanto Sucipto Mulai tanggal 01 September 2026
2026-10-06 12:26:59 | 7201250141 | 044/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-04 | 1 | PERSONEL ON CALL | Helper Local (non Skilled) | 0 | man-days | 2026-09-04 | PERSONNEL ON-CALL Helper Local (non Skilled) Tenaga Flagman Mulai tgl 4 September 2026
2026-10-06 12:57:19 | 7201250141 | 045/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | crane min 70 ton, call out, (hanya unit) | 1 | Day | 2026-09-01 | Crane Sany 100 ton menggantikan Crane Tadano 70 ton yang rusak Operasi Mulai 01 September 2026
2026-10-06 12:57:19 | 7201250141 | 045/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Vacuum Truck , Call out, Cap 5000 ltr c/w vacuum pump & acessories, call out, (hanya unit) | 1 | Day | 2026-09-01 | Vacuum Truck , Call out, Cap 5000 ltr Operasi Mulai 01 September 2026
2026-10-06 19:05:27 | 7201250141 | 050/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | PROVISIONAL SUM | At Cost + Fee 15% | 1 | AU | 2026-09-01 | Provisional SUM Akomodasi untuk crew well services di penginapan Yellow Toili Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | ADDITIONAL CAMP SERVICES | Portacamp - Office Camp, ukuran 40 FT | 0 | Month | 2026-09-01 | Support Well Services Senoro Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | ADDITIONAL CAMP SERVICES | Portacamp - Living camp,ukuran 40FT (4 sleepers) | 0 | Month | 2026-09-01 | Support Well Services Senoro Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 3 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Genset, cap min 80 KVA, silent type, include maintenance | 0 | Month | 2026-09-01 | Operasi Shift Siang Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 4 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Genset, cap min 80 KVA, silent type, include maintenance | 0 | Month | 2026-09-01 | Operasi Shift Malam Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 5 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories | 0 | Month | 2026-09-01 | Operasi Shift Malam Mulai 01 September 2026
2026-10-07 06:14:37 | 7201250141 | 047/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 6 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Light Tower & Lamp 1000 Watt, c/w cable,plug & acessories | 0 | Month | 2026-09-01 | Operasi Shift Malam Mulai 01 September 2026
2026-10-07 08:42:47 | 7201250141 | 039/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Mobilization/ Demobilization of Rental Equipments (Genset/ Air Compressor/ Light Tower/ Fuel Tank, etc) to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-08 | Tronton Muat Mesin Genset dan Light tower dari Lamo ke Cluster B
2026-10-07 08:42:47 | 7201250141 | 039/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 2 | HEAVY TRANSPORTATION & EQUIPMENT RENTAL | Mobilization/ Demobilization of Rental Equipments (Genset/ Air Compressor/ Light Tower/ Fuel Tank, etc) to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-08 | Tronton Muat Tenda, Meja, Kursi dan Counter Weight dari Lamo ke Cluster B
2026-10-07 09:01:02 | 7201250141 | 039A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 1 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-08 | Trailler 40 feet Mobilisasi Portacamp Office dari Lamo ke Cluster B
2026-10-07 09:01:02 | 7201250141 | 039A/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-08 | 2 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-08 | Trailler 40 feet Mobilisasi Portacamp Sleeper dari Lamo ke Cluster B
2026-10-07 09:33:16 | 7201250141 | 039B/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-14 | 1 | LAND TRANSPORTATION | trailer 20" atau tronton 15 ton, call out, Cluster Senoro 6 - Cluster B atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-14 | Tronton DN 8639 CH muat tenda, meja - kursi dan Counter Weight
2026-10-07 09:33:16 | 7201250141 | 039B/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-14 | 2 | LAND TRANSPORTATION | trailer 20" atau tronton 15 ton, call out, Cluster Senoro 6 - Cluster B atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-14 | Tronton DN 8140 CA Muat Mesin Genset 2 unit, Lighting tower 2 unit dan panel Listrik
2026-10-07 09:33:16 | 7201250141 | 039B/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-14 | 3 | LAND TRANSPORTATION | trailer 40" atau tronton 15 ton, call out, Cluster Senoro 6 - Cluster B atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-14 | Trailler 40 feet DN 8785 RA muat equipment well services
2026-10-07 09:33:16 | 7201250141 | 039B/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-14 | 4 | LAND TRANSPORTATION | trailer 40" atau tronton 15 ton, call out, Cluster Senoro 6 - Cluster B atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-14 | Trailler 40 feet DN 8950 RA muat Portacamp sleeper 40 feet
2026-10-07 09:33:16 | 7201250141 | 039B/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-14 | 5 | LAND TRANSPORTATION | trailer 40" atau tronton 15 ton, call out, Cluster Senoro 6 - Cluster B atau sebaliknya c/w BBM & driver | 1 | AU | 2026-08-14 | Trailler 40 feet DN 8959 RA muat Portacamp Office 40 feet
2026-10-07 10:35:04 | 7201250141 | 039C/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-20 | 1 | LAND TRANSPORTATION | trailer 20" atau tronton 15 ton, call out, Cluster Senoro 2 - Cluster Senoro 6 atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-20 | tronton DN 8639 CH muat tenda, meja-kursi, Counter Weight ABC
2026-10-07 10:35:04 | 7201250141 | 039C/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-20 | 2 | LAND TRANSPORTATION | trailer 20" atau tronton 15 ton, call out, Cluster Senoro 2 - Cluster Senoro 6 atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-20 | Tronton DN 8140 CA Muat Mesin Genset 2 unit, Lighting tower 2 unit dan panel Listrik
2026-10-07 10:35:04 | 7201250141 | 039C/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-20 | 3 | LAND TRANSPORTATION | trailer 40" atau tronton 15 ton, call out, Cluster Senoro 2 - Cluster Senoro 6 atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-20 | Trailler 40 feet DN 8950 RA muat Equipment Well Services
2026-10-07 10:35:04 | 7201250141 | 039C/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-20 | 4 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-20 | Trailler 40 feet DN 8785 RA Demobilisasi portacamp Sleeper 40 feet dari Senoro 2 ke Lamo
2026-10-07 10:35:04 | 7201250141 | 039C/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-20 | 5 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | AU | 2026-08-20 | Trailler 40 feet DN 8959 RA Demobilisasi portacamp Office 40 feet dari Senoro 2 ke Lamo
2026-10-07 11:29:01 | 7201250141 | 039D/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-23 | 1 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-23 | Trailler 40 feet DN 8785 RA mobilisasi Portacamp office dari Lamo ke Senoro Mulai tgl 23 Agustus 2026
2026-10-07 11:29:01 | 7201250141 | 039D/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-23 | 2 | ADDITIONAL CAMP SERVICES | Mobilization/ Demobilization 40 ft Additional Camp to/from Company Wellsite/ Contractor base | 1 | Trip | 2026-08-23 | Trailler 40 feet DN 8959 RA mobilisasi Portacamp Sleeper dari Lamo ke Senoro Mulai tgl 23 Agustus 2026
2026-10-07 11:29:01 | 7201250141 | 039D/BSS-JOB/WS/VIII/2026 | Luwuk | 2026-08-23 | 3 | LAND TRANSPORTATION | trailer 20" atau tronton 15 ton, call out, Cluster Senoro 2 - Contractor's alternative jetty atau sebaliknya c/w BBM & driver | 1 | Trip | 2026-08-29 | Tronton 20 feet DN 9639 CH dari Lamo ke Senoro 2 pindahkan Barang TGE di lokasi senoro 2 Mulai tgl 29 Agustus 2026
2026-10-07 11:58:01 | 7201250141 | 038/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | ADDITIONAL CAMP SERVICES | Food & beverage, main course | 0 | AU | 2026-09-01 | DDITIONAL CAMP SERVICES, Operational Consumption
2026-10-07 11:58:01 | 7201250141 | 038/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | ADDITIONAL CAMP SERVICES | Food & beverage, snack coffee/ tea & desert | 0 | AU | 2026-09-01 | ADDITIONAL CAMP SERVICES, Operational side consumption
2026-10-10 08:58:33 | 7201250141 | 046/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-09-01 | Kendaraan Inova DN 1259 CL Support Well Services Mulai tanggal 01 September 2026
2026-10-10 08:58:33 | 7201250141 | 046/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 2 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-09-01 | Kendaraan Inova DN 1257 CL Support Well Services Mulai tanggal 01 September 2026
2026-10-10 08:58:33 | 7201250141 | 046/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 3 | CAR & TANSPORTATION | Station wagon 7 seater diesel engine + driver + BBM, | 1 | Day | 2026-09-27 | Kendaraan Inova DN 1258 CL Support Well Services Mulai tanggal 27 September 2026
2026-10-10 08:58:33 | 7201250141 | 046/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 4 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 1 | Day | 2026-09-01 | Kendaraan Double Cabin Hilux DN 8916 CH Support Well Services Mulai tanggal 01 September 2026
2026-10-10 08:58:33 | 7201250141 | 046/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 5 | CAR & TANSPORTATION | Double cabin 4x4, diesel engine + driver + BBM, | 1 | Day | 2026-09-01 | Kendaraan Double Cabin Hilux DN 8917 CH Support Well Services Mulai tanggal 01 September 2026
2026-10-10 12:30:03 | 7201250141 | 048/BSS-JOB/WS/IX/2026 | Luwuk | 2026-09-01 | 1 | ADDITIONAL CAMP SERVICES | Laundry services | 0 | Kg | 2026-09-01 | Laundry services, Untuk Personel Serco Mulai 01 September 2026